## Sheet1
| 2013 |  |  | 2014
| October | November | December | January | February | March | April | May
background research on possible projects | bar: 2013 October to 2013 November
contact Lowell Observatory researcher | bar: 2013 November
project proposal and plan | bar: 2013 November to 2014 January
literature review | bar: 2013 December to 2014 February
introduction and background section draft | bar: 2014 January
curve-fitting and other software development | bar: 2013 December to 2014 January
data collection | bar: 2014 January
data analysis | 2014 January: first round finished in January
curve-fitting chapter and appendix | bar: 2014 January
initial presentations | bar: 2014 January
proposal for further work | bar: 2014 January
revisions and further additions | bar: 2014 February to 2014 April
presentation prep | 2014 May: presention May 16
revisions | 2014 May: by May 12, 2013
submit final version | 2014 May: by May 12, 2013